## S1
diameter
DANA KHOLA HYDROPOWER PROJECT (34.8MW) | [12 empty] | 6.2
MANANG,NEPAL | [10 empty] | pie | radius |  | payline | shortcrete
Structure: Tunnel | [10 empty] | 3.14 | 3.2 | 3.1 | 0.05 | 0.05
S.N | Description | No | Length (m) | Breadth (m) | Height (m) | Perimeter (m) | Area (m²) | Quantity | Total Qty | Unit
8.1 | Earthwork in excavation rock at Tunnel including haulage-Underground.
| a) Hard rock | [7 empty] | 35.9168 | m3
| Typical section type-S1 | 1 | 1 |  |  |  | 35.9168 | 35.9168 |  | m3
8.4 | Supply and laying of thick fiber reinforced shortcrete as per specification or as directed by engineer. | [7 empty] | 16.4125 | m2 |  | shortcrete radius
| a)50mm | 1 | 1 |  |  | 16.4125 | 16.4125 | 16.4125 |  | m2 |  | 3.125
8.5 | Providing and placing machine mixed non structural cement concrete including compaction curing, testing all complete as per specification and drawing. | [7 empty] | 0.64 | m3
| a) 1:1:2 (Invert concrete) | [9 empty] | thickness
| Typical section type-S1 | 1 | 1 | 3.2 |  |  |  | 0.64 |  | m3 | 0.2 |  | Height
| Supply and installation of wire mesh (100x100x8) as per specification or as directed by engineer. | [7 empty] | 16.491 | m2 |  | wire mesh radius | 3.3
|  | 1 | 1 |  |  | 16.491 | 16.491 | 16.491 |  | m2 |  | 3.15
8.6 | Supply and installation of 3m long, 20mm dia. Grouted rockbolt at the spacing @2.1m c/c circumferencial and 2.1m c/c longitudinally as an immediate support including all required equipment, materials, drillings, flushing, grouting and as per specification or as directed by engineer. | [7 empty] | 8.244 | nos. | c/c distance | Height
| Typical section type-S1 | 1 |  |  |  | 16.2125 |  | 8.244 |  | nos. | 2.1 | 3.2
8.9 | Providing and laying reinforcement including cutting, bending, binding, fixing in position etc. all complete as per specification and drawing. | [7 empty] | 0.02512 | ton

## S2
DANA KHOLA HYDROPOWER PROJECT (34.8MW)
MANANG,NEPAL | [10 empty] | pie | radius | R | payline | shortcrete
Structure: Tunnel | [10 empty] | 3.14 | 3.2 | 3.1 | 0.05 | 0.05
S.N | Description | No | Length (m) | Breadth (m) | Height (m) | Perimeter (m) | Area (m²) | Quantity | Total Qty | Unit
8.1 | Earthwork in excavation rock at Tunnel including haulage-Underground.
| a) Hard rock | [7 empty] | 35.9168 | m3
| Typical section type-S2 | 1 | 1 |  |  |  | 35.9168 | 35.9168 |  | m3
8.4 | Supply and laying of thick fiber reinforced shortcrete as per specification or as directed by engineer. | [7 empty] | 16.4125 | m2 |  | shortcrete radius
| a)50mm | 1 | 1 |  |  | 16.4125 | 16.4125 | 16.4125 |  | m2 |  | 3.125
8.5 | Providing and placing machine mixed non structural cement concrete including compaction curing, testing all complete as per specification and drawing. | [7 empty] | 0.64 | m3
| a) 1:1:2 (Invert concrete) | [9 empty] | thickness
| Typical section type-S2 | 1 | 1 | 3.2 |  |  | 0.64 | 0.64 |  | m3 | 0.2 |  | Height
| Supply and installation of wire mesh (100x100x8) as per specification or as directed by engineer. | [7 empty] | 16.491 | m2 |  | wire mesh radius | 3.3
|  | 1 | 1 |  |  | 16.491 | 16.491 | 16.491 |  | m2 |  | 3.15
8.6 | Supply and installation of 3.5m long, 20mm dia. Grouted rockbolt at the spacing @1.7m c/c circumferencial and 1.7m c/c longitudinally as an immediate support including all required equipment, materials, drillings, flushing, grouting and as per specification or as directed by engineer. | [7 empty] | 9.9485 | nos. | c/c distance | height
| Typical section type-S2 | 1 |  |  |  | 16.2125 |  | 9.9485 |  | nos. | 1.7 | 3.2
8.9 | Providing and laying reinforcement including cutting, bending, binding, fixing in position etc. all complete as per specification and drawing. | [7 empty] | 0.02512 | ton

## S3
DANA KHOLA HYDROPOWER PROJECT (34.8MW)
MANANG,NEPAL | [10 empty] | pie | radius | R | payline | shortcrete | concrete lining
Structure: Tunnel | [10 empty] | 3.14 | 3.24 | 3.1 | 0.05 | 0.09 | 0.3
S.N | Description | No | Length (m) | Breadth (m) | Height (m) | Perimeter (m) | Area (m²) | Quantity | Total Qty | Unit
8.1 | Earthwork in excavation rock at Tunnel including haulage-Underground.
| a) Hard rock | [7 empty] | 36.5692 | m3
| Typical section type-S3 | 1 | 1 |  |  |  | 36.5692 | 36.5692 |  | m3
8.4 | Supply and laying of thick fiber reinforced shortcrete as per specification or as directed by engineer. | [7 empty] | 17.4173 | m2 |  | shortcrete radius
| a)90mm | 1 | 1 |  |  | 17.4173 | 17.4173 | 17.4173 |  | m2 |  | 3.445
8.5 | Providing and placing machine mixed non structural cement concrete including compaction curing, testing all complete as per specification and drawing. | [7 empty] | 6.4375 | m3
| a) 1:1:2 (Invert concrete) | [9 empty] | thickness
| Typical section type-S3 | 1 | 1 | 6.98 |  |  | 1.396 | 1.396 |  | m3 | 0.2
| b) Concrete lining | [9 empty] | concrete lining | radius
| 300mm | 1 | 1 |  |  |  | 16.805 | 5.0415 |  | m3 | 0.3 | 3.25
Height
| Supply and installation of wire mesh (100x100x8) as per specification or as directed by engineer. | [7 empty] | 16.6166 | m2 |  | wire mesh radius | 3.3
|  | 1 | 1 |  |  | 16.6166 | 16.6166 | 16.6166 |  | m2 |  | 3.19
8.6 | Supply and installation of 3.5m long, 25mm dia. Grouted rockbolt at the spacing @1.5m c/c circumferencial and 1.5m c/c longitudinally as an immediate support including all required equipment, materials, drillings, flushing, grouting and as per specification or as directed by engineer. | [7 empty] | 11.8115 | nos. | c/c distance | Height
| Typical section type-S3 | 1 |  |  |  | 17.2173 |  | 11.8115 |  | nos. | 1.5 | 3.2
8.9 | Providing and laying reinforcement including cutting, bending, binding, fixing in position etc. all complete as per specification and drawing. | [7 empty] | 0.25267 | ton
8.1 | Providing, preparing and installing form work and removing after completion as per specification. | [7 empty] | 15.934 | m2
| a) conrete linning | 1 | 1 |  |  | 15.934 |  | 15.934 |  | m2

## S4
DANA KHOLA HYDROPOWER PROJECT (34.8MW)
MANANG,NEPAL | [10 empty] | pie | radius | R | payline | shortcrete | concrete lining
Structure: Tunnel | [10 empty] | 3.14 | 3.27 | 3.1 | 0.05 | 0.12 | 0.3
S.N | Description | No | Length (m) | Breadth (m) | Height (m) | Perimeter (m) | Area (m²) | Quantity | Total Qty | Unit
8.1 | Earthwork in excavation rock at Tunnel including haulage-Underground.
| a) Hard rock | [7 empty] | 37.0619 | m3
| Typical section type-S4 | 1 | 1 |  |  |  | 37.0619 | 37.0619 |  | m3
8.4 | Supply and laying of thick fiber reinforced shortcrete as per specification or as directed by engineer. | [7 empty] | 17.4644 | m2 |  | shortcrete radius
| a)120mm | 1 | 1 |  |  | 17.4644 | 17.4644 | 17.4644 |  | m2 |  | 3.46
8.5 | Providing and placing machine mixed non structural cement concrete including compaction curing, testing all complete as per specification and drawing. | [7 empty] | 6.4495 | m3
| a) 1:1:2 (Invert concrete) | [9 empty] | thickness
| Typical section type-S4 | 1 | 1 | 7.04 |  |  | 1.408 | 1.408 |  | m3 | 0.2
| b) Concrete lining | [9 empty] | concrete lining | radius
| 300mm | 1 | 1 |  |  | 16.805 | 16.805 | 5.0415 |  | m3 | 0.3 | 3.25
Height
| Supply and installation of wire mesh (100x100x8) as per specification or as directed by engineer. | [7 empty] | 16.7108 | m2 |  | wire mesh radius | 3.3
|  | 1 | 1 |  |  | 16.7108 | 16.7108 | 16.7108 |  | m2 |  | 3.22
8.6 | Supply and installation of 4m long, 25mm dia. Grouted rockbolt at the spacing @1.3m c/c circumferencial and 1.3m c/c longitudinally as an immediate support including all required equipment, materials, drillings, flushing, grouting and as per specification or as directed by engineer. | [7 empty] | 13.5111 | nos. | c/c distance | Height
| Typical section type-S2 | 1 |  |  |  | 17.2644 |  | 13.5111 |  | nos. | 1.3 | 3.2
8.9 | Providing and laying reinforcement including cutting, bending, binding, fixing in position etc. all complete as per specification and drawing. | [7 empty] | 0.25314 | ton
8.1 | Providing, preparing and installing form work and removing after completion as per specification. | [7 empty] | 15.934 | m2
| a) conrete linning (typical section type S4) | 1 | 1 |  |  | 15.934 | 15.934 | 15.934 |  | m2

## S5
DANA KHOLA HYDROPOWER PROJECT (34.8MW)
MANANG,NEPAL | [10 empty] | pie | radius | R | payline | shortcrete | concrete lining
Structure: Tunnel | [10 empty] | 3.14 | 3.3 | 3.1 | 0.05 | 0.15 | 0.3
S.N | Description | No | Length (m) | Breadth (m) | Height (m) | Perimeter (m) | Area (m²) | Quantity | Total Qty | Unit
8.1 | Earthwork in excavation rock at Tunnel including haulage-Underground.
| a) Hard rock | [7 empty] | 37.5573 | m3
| Typical section type-S5 | 1 | 1 |  |  |  | 37.5573 | 37.5573 |  | m3
8.4 | Supply and laying of thick fiber reinforced shortcrete as per specification or as directed by engineer. | [7 empty] | 17.5115 | m2 |  | shortcrete radius
| a)150mm | 1 | 1 |  |  | 17.5115 | 17.5115 | 17.5115 |  | m2 |  | 3.475
8.5 | Providing and placing machine mixed non structural cement concrete including compaction curing, testing all complete as per specification and drawing. | [7 empty] | 6.4615 | m3
| a) 1:1:2 (Invert concrete) | [9 empty] | thickness
| Typical section type-S5 | 1 | 1 | 7.1 |  |  | 1.42 | 1.42 |  | m3 | 0.2
| b) Concrete lining | [9 empty] | concrete lining | radius
| 300mm | 1 | 1 |  |  | 16.805 | 16.805 | 5.0415 |  | m3 | 0.3 | 3.25
Height
| Supply and installation of wire mesh (100x100x8) as per specification or as directed by engineer. | [7 empty] | 16.805 | m2 |  | wire mesh radius | 3.3
|  | 1 | 1 |  |  | 16.805 | 16.805 | 16.805 |  | m2 |  | 3.25
8.6 | Supply and installation of 4m long, 25mm dia. Grouted rockbolt at the spacing @1m c/c circumferencial and 1m c/c longitudinally as an immediate support including all required equipment, materials, drillings, flushing, grouting and as per specification or as directed by engineer. | [7 empty] | 17.3115 | nos. | c/c distance | Height
| Typical section type-S5 | 1 |  |  |  | 17.3115 |  | 17.3115 |  | nos. | 1 | 3.2
8.9 | Providing and laying reinforcement including cutting, bending, binding, fixing in position etc. all complete as per specification and drawing. | [7 empty] | 0.25361 | ton
8.1 | Providing, preparing and installing form work and removing after completion as per specification. | [7 empty] | 15.934 | m2
| a) conrete linning (typical section type S5) | 1 | 1 |  |  | 15.934 | 15.934 | 15.934 |  | m2

## S6
DANA KHOLA HYDROPOWER PROJECT (34.8MW)
MANANG,NEPAL | [10 empty] | pie | radius | R | payline | shortcrete | concrete lining
Structure: Tunnel | [10 empty] | 3.14 | 3.4 | 3.1 | 0.05 | 0.25 | 0.4
S.N | Description | No | Length (m) | Breadth (m) | Height (m) | Perimeter (m) | Area (m²) | Quantity | Total Qty | Unit
8.1 | Earthwork in excavation rock at Tunnel including haulage-Underground.
| a) Hard rock | [7 empty] | 39.2292 | m3
| Typical section type-S6 | 1 | 1 |  |  |  | 39.2292 | 39.2292 |  | m3
8.4 | Supply and laying of thick fiber reinforced shortcrete as per specification or as directed by engineer. | [7 empty] | 17.9825 | m2 |  | shortcrete radius
| a)250mm | 1 | 1 |  |  | 17.9825 | 17.9825 | 17.9825 |  | m2 |  | 3.625
8.5 | Providing and placing machine mixed non structural cement concrete including compaction curing, testing all complete as per specification and drawing. | [7 empty] | 8.2848 | m3
| a) 1:1:2 (Invert concrete) | [9 empty] | thickness
| Typical section type-S6 | 1 | 1 | 7.5 |  |  | 1.5 | 1.5 |  | m3 | 0.2
| b) Concrete lining | [9 empty] | concrete lining | radius
| 400mm | 1 | 1 |  |  | 16.962 | 16.962 | 6.7848 |  | m3 | 0.4 | 3.3
Height
| Supply and installation of wire mesh (100x100x8) as per specification or as directed by engineer. | [7 empty] | 17.119 | m2 |  | wire mesh radius | 3.3
|  | 1 | 1 |  |  | 17.119 | 17.119 | 17.119 |  | m2 |  | 3.35
8.6 | Supply and installation of 4m long, 25mm dia. Grouted rockbolt at the spacing @1m c/c circumferencial and 1m c/c longitudinally as an immediate support including all required equipment, materials, drillings, flushing, grouting and as per specification or as directed by engineer. | [7 empty] | 17.7825 | nos. | c/c distance | Height
| Typical section type-S6 | 1 |  |  |  | 17.7825 |  | 17.7825 |  | nos. | 1 | 3.2
8.9 | Providing and laying reinforcement including cutting, bending, binding, fixing in position etc. all complete as per specification and drawing. | [7 empty] | 0.32518 | ton
8.1 | Providing, preparing and installing form work and removing after completion as per specification. | [7 empty] | 15.934 | m2
| a) conrete linning (typical section type S6) | 1 | 1 |  |  | 15.934 | 15.934 | 15.934 |  | m2